## Taul1
Test cases for users
Test 1
Name | 1. New user registers and looks for instructions.
Design Date | 2025-04-16
Preconditions | The app is installed on the user's device
Executed by: | Mika Laakkonen
Execution date: | 2025-04-26
Step | Action | Expected System Response | Pass / Fail | Comment
| Open application | User is greeted with welcome screen | Pass
| User clicks welcome screen | User is taken to language selection | Pass
| User selects language and clicks ready | User language selection instantly updates UI language and user is directed to main menu | Pass
| User selects register | User is directed to registration page | Pass
| User inputs form information and presses register | User is taken to start session view | Pass
| User clicks help icon on the navigation bar | User is directed to help section | Pass
Post-condition | User found usage instructions.
Test 2
Name | 2. New user registers and tries to match themselves.
Design Date | 2025-04-16
Preconditions | The app is installed on the user's device
Executed by: | Mika Laakkonen
Execution date: | 2025-04-26
Step | Action | Expected System Response | Pass / Fail | Comment
| Open application | User is greeted with welcome screen | Pass
| User clicks welcome screen | User is directed to language selection | Pass
| User selects language | User language selection instantly updates UI language and user is directed to main menu | Pass
| User selects register | User is directed to registration page | Pass
| User enters personal info (different email from last time) | User registers successfully and is directed to start session page. | Pass
| User selects start session | User is directed to session page | Pass
| User chooses their preferred interests | Interests are selected and stored in the app's local storage | Pass
| User selects ready | User is directed to match view page and is shown their match | Pass
Post-condition | New user was successfully matched.
Test 3.
Name | 3. Existing user logs in and tries to match themselves.
Design Date | 2025-04-16
Preconditions | The app is installed on the user's device and user has an existing account.
Executed by: | Mika Laakkonen
Execution date: | 2025-04-26
Step | Action | Expected System Response | Pass / Fail | Comment
| Open application | User is greeted with welcome screen | Pass
| User clicks welcome screen | User is taken to language selection | Pass
| User selects language | User language selection instantly updates UI language and user is directed to main menu | Pass
| User selects login | User is directed to login page | Pass
| User inputs login information and selects "log in" | User directed to start session page | Pass
| User selects start session | User is directed to session page | Pass
| User chooses their preferred interests | Interests are selected and stored in the app's local storage | Pass
| User selects ready | User is directed to match view page and is shown their match | Pass
Post-condition | Existing user was successfully matched.
Test 4
Name | 4. New user changes their phone number after registration.
Design Date | 2025-04-16
Preconditions | The app is installed on the user's device
Executed by: | Mika Laakkonen
Execution date: | 2025-04-26
Step | Action | Expected System Response | Pass / Fail | Comment
| Open application | User is greeted with welcome screen | Pass
| User clicks welcome screen | User is taken to language selection | Pass
| User selects language | User language selection instantly updates UI language and user is directed to main menu | Pass
| User selects register | User is directed to registration page | Pass
| User inputs form information and presses register | User is taken to start session page | Pass
| User clicks profile icon on navigation bar | User is directed to profile page | Pass
| User clicks edit icon on profile view | User is directed to edit profile page | Pass
| User inputs new phone number and clicks back icon | User is informed about the saved changes with a pop up | Pass
| User clicks "okay" on the pop up | User directed to profile page | Pass
Post-condition | New user successfully changed their phone number.
Test 5.
Name | 5. Existing user changes their app language after login.
Design Date | 2025-04-16
Preconditions | The app is installed on the user's device and user has an existing account.
Executed by: | Mika Laakkonen
Execution date: | 2025-04-26
Step | Action | Expected System Response | Pass / Fail | Comment
| Open application | User is greeted with welcome screen | Pass
| User clicks welcome screen | User is taken to language selection | Pass
| User selects language | User language selection instantly updates UI language and user is directed to main menu | Pass
| User selects login | User is directed to login page | Pass
| User inputs login information and selects "log in" | User directed to start session page | Pass
| User clicks profile icon on navigation bar | User is directed to profile view | Pass
| User clicks the edit icon | User is directed to edit profile view | Pass
| User selects "change language" | User is directed to page where they can select a language | Pass
| User selectes their preferred language and clicks ready or goes back | User is taken back to edit profile and their app is now in their selected language | Pass
Post-condition | Existing user successfully changed their language after login.
Test 6.
Name | 6. Guest tries to match themselves with someone.
Design Date | 2025-04-16
Preconditions | The app is installed on the user's device.
Executed by: | Mika Laakkonen
Execution date: | 2025-04-26
Step | Action | Expected System Response | Pass / Fail | Comment
| Open application | User is greeted with welcome screen | Pass
| User clicks welcome screen | User is taken to language selection | Pass
| User selects language | User language selection instantly updates UI language and user is directed to main menu | Pass
| User selects guest | User is directed to quest page | Pass
| User inputs their phone number and selects continue | User is directed to start session page | Pass
| User selects start session | User is directed to session page | Pass
| User chooses their preferred interests | Interests are selected and stored in the app's local storage | Pass
| User selects ready | User is directed to match view page and is shown their match | Pass
Post-condition | Guest user was successfully matched.
Test 7.
Name | 7. Admin logs in (predefined credentials) and removes a match
Design Date | 2025-04-16
Preconditions | The app is installed on the user's device and user has been given admin credentials.
Executed by: | Mika Laakkonen
Execution date: | 2025-04-26
Step | Action | Expected System Response | Pass / Fail | Comment
| Open application | User is greeted with welcome screen | Pass
| User clicks welcome screen | User is taken to language selection | Pass
| User selects language | User language selection instantly updates UI language and user is directed to main menu | Pass
| User selects login | User is directed to login page | Pass
| User inputs admin credentials and selects continue | User is directed to start session page | Pass
| User clicks profile icon on navigation bar | User is directed to profile view | Pass
| User selects "pair history" | User is directed to match administration view | Pass
| User removes a match | A match is successfully removed from the page and user is informed about it | Pass
Post-condition | Admin successfully removed a match.
Test 8.
Name | 8. Admin logs in and removes a user
Design Date | 2025-04-16
Preconditions | The app is installed on the user's device and user has been given admin credentials.
Executed by: | Mika Laakkonen
Execution date: | 2025-04-26
Step | Action | Expected System Response | Pass / Fail | Comment
| Open application | User is greeted with welcome screen | Pass
| User clicks welcome screen | User is taken to language selection | Pass
| User selects language | User language selection instantly updates UI language and user is directed to main menu | Pass
| User selects login | User is directed to login page | Pass
| User inputs admin credentials and selects continue | User is directed to start session page | Pass
| User clicks profile icon on navigation bar | User is directed to profile view | Pass
| User selects "users" | User is directed to user administration view | Pass
| User removes a user | A user is successfully removed from the page and user is informed about it | Pass
Post-condition | Admin successfully removed a user.
Test 9.
Name | 7. New user registers, logs out successfully, and logs back in.
Design Date | 2025-04-16
Preconditions | The app is installed on the user's device.
Executed by: | Mika Laakkonen
Execution date: | 2025-04-26
Step | Action | Expected System Response | Pass / Fail | Comment
| Open application | User is greeted with welcome screen | Pass
| User clicks welcome screen | User is taken to language selection | Pass
| User selects language | User language selection instantly updates UI language and user is directed to main menu | Pass
| User selects register | User is directed to registration page | Pass
| User inputs form information and presses register | User is taken to start session page | Pass
| User clicks logout icon on navigation bar | User is directed to login methods screen | Pass
| User selects login | User is directed to login page | Pass
| User inputs login information and selects "log in" | User directed to start session page | Pass
Post-condition | New user success logged back in.
Test 10
Name | 10. Existing user tries to make a new account by registering with an invalid email, user tries to log in with an incorrect password, user logs in with correct credentials, user begins a session and does not choose any interests and selects “ready”.
Design Date | 2025-04-16
Preconditions | The app is installed on the user's device
Executed by: | Mika Laakkonen
Execution date: | 2025-04-26
Step | Action | Expected System Response | Pass / Fail | Comment
| Open application | User is greeted with welcome screen | Pass
| User clicks welcome screen | User is taken to language selection | Pass
| User selects language | User language selection instantly updates UI language and user is directed to main menu | Pass
| User selects register | User is directed to registration page | Pass
| User inputs form information with invalid email adress selects register | User is informed about the invalid email format | Pass
| User clicks ok on error message | Error message closes | Pass
| User clicks back icon | User is directed to main menu | Pass
| User selects login and inputs wrong password | User is informed about the invalid password | Pass
| User clicks ok on error message | Error message closes | Pass
| User enters correct login information | User is directed to start session page | Pass
| User clicks start session | User is directed to category page | Pass
| User doesn't choose any category and selects "ready" | User is informed that they have to choose at least one category | Pass
Post-condition | User was displayed correct error messages after each error.